## Roadmap Tasks
Task ID | Task Name | Start Date | End Date | Duration (Days) | Dependencies
1 | Hotel Supply: Connectivity and Local Contracts | 2026-01-15 | 2026-07-31 | 197 | -
2 | Pricing rules - BAU | 2026-01-01 | 2026-08-31 | 242 | -
3 | Local Contracts Go Live (OJ + Darwin Flow) | 2026-05-01 | 2026-05-31 | 30 | 1
4 | Phase 2 Destinations Enabling - Brussels, Copenhagen, Ibiza | 2026-02-01 | 2026-03-15 | 42 | -
5 | Phase 3 Destinations Enabling - Amsterdam, Athens, Dublin, Glasgow, Manchester | 2026-03-01 | 2026-03-23 | 22 | 4
6 | Phase 4 Destinations Enabling - Barcelona, Istanbul, Malta | 2026-04-01 | 2026-04-23 | 22 | 5
7 | Phase 5 Destinations Enabling - Boston, Chicago, Jersey, Marrakech, Miami | 2026-05-01 | 2026-05-26 | 25 | 6
8 | Tech / Platform work | 2026-03-15 | 2026-08-15 | 153 | -
9 | Automate product setup | 2026-04-01 | 2026-07-31 | 121 | 8
10 | PS: Codegen Gaps | 2026-05-01 | 2026-08-31 | 122 | -
11 | Promotions calendar | 2026-04-15 | 2026-06-30 | 76 | 8
12 | Remove Dynamic Profile Creation completely or remove from Mik's team | 2026-03-01 | 2026-04-15 | 45 | -
13 | Automate Agresso set up for supplier info (to migrate work from Mik's team to WNS) | 2026-04-01 | 2026-06-15 | 75 | 9
14 | Product Setup for Transfers | 2026-05-15 | 2026-07-15 | 61 | 9
15 | Set up & content for Cars | 2026-05-01 | 2026-06-30 | 60 | 9
16 | Detailed plan for locally held contract dual run go live (in OJ) | 2026-03-15 | 2026-04-30 | 46 | 1
17 | Revise usefulness of Splunk dashboards | 2026-04-01 | 2026-05-15 | 44 | 8
18 | Set up monitoring and alerting | 2026-05-01 | 2026-06-30 | 60 | 17
19 | Ensure observability is sufficient to allow troubleshooting of alerts | 2026-06-01 | 2026-07-31 | 60 | 18
20 | Set up and progressively extend automated regression testing in TBX | 2026-04-15 | 2026-08-31 | 138 | 8
21 | Add Vegas as a Destination | 2026-06-15 | 2026-07-31 | 46 | 7
22 | LC - TravelGate Integration (OJ/TBX) | 2026-05-01 | 2026-08-31 | 122 | 8
23 | Training for Destinations team | 2026-07-01 | 2026-08-15 | 45 | 7
24 | Training for WNS | 2026-07-15 | 2026-08-31 | 47 | 13
25 | Training for Pricing | 2026-07-15 | 2026-08-31 | 47 | 2
26 | Training for BAU testers | 2026-07-01 | 2026-08-15 | 45 | 20
27 | Training for Operations (Local) | 2026-07-15 | 2026-08-31 | 47 | 3
28 | Training for Contentful (Local/PS) | 2026-07-01 | 2026-08-15 | 45 | 9
29 | Headline Price + Local Fees API feeds for Hotel Only and Packages (DP Flight + Hotel) | 2026-02-01 | 2026-04-30 | 88 | 2
30 | Modular Price Comparison: Dilution Rules - Ability to flex package price | 2026-03-01 | 2026-05-31 | 91 | 29
31 | Markup Scheme / Discount Scheme Adjustment based on bundled or individual component cost | 2026-04-01 | 2026-06-30 | 90 | 30
32 | Modular Price Comparison: Close the Gap | 2026-03-15 | 2026-05-15 | 61 | 29
33 | Hotel Content Model | 2026-04-01 | 2026-07-31 | 121 | 9
34 | Product Setup process optimisation | 2026-05-01 | 2026-07-15 | 75 | 9
35 | CMA Headline Price | 2026-05-15 | 2026-08-31 | 108 | 29
36 | Flight Dilution rules | 2026-04-15 | 2026-07-31 | 107 | 30
37 | Bundles core pricing rules + pricing and markup enhancements (integration of private fares) | 2026-04-01 | 2026-08-31 | 152 | 31
38 | Minimum Margin Protection | 2026-05-15 | 2026-08-31 | 108 | 37
39 | Automated content loading solution - Automation of Product Loading using CodeGen AI | 2026-05-01 | 2026-08-15 | 106 | 10
40 | IBS Connectivity & Add Vegas as a destination | 2026-06-01 | 2026-08-31 | 91 | 21
41 | LC - Smart Contract Loading | 2026-06-01 | 2026-08-31 | 91 | 33
42 | Get relevant hotel recommendations - Discovery Phase | 2026-04-01 | 2026-05-31 | 60 | -
43 | Get relevant hotel recommendations - Implementation | 2026-06-01 | 2026-08-31 | 91 | 42
44 | Surface Best Room Offer - Prepare Discovery | 2026-04-15 | 2026-06-15 | 61 | -
45 | LC - Supplier Contracts & Communication (PDF) | 2026-03-01 | 2026-07-31 | 152 | 1
46 | LC - Supplier Contracts & Communication (Template - Blocker) | 2026-04-01 | 2026-06-30 | 90 | 45
47 | Data Migration & Inventory | 2026-05-01 | 2026-08-31 | 122 | 46
48 | Create Tritium IDs in Travelbox and Hotel loading (10,500 hotels live by end July) | 2026-05-15 | 2026-07-31 | 77 | 47
49 | LC - Finance & Agresso | 2026-05-01 | 2026-08-31 | 122 | 13
50 | IBS Connectivity - Setup | 2026-04-01 | 2026-07-31 | 121 | 8
51 | Manual Hotel Scaling | 2026-02-01 | 2026-04-30 | 88 | -
52 | Automated Hotel Scaling | 2026-05-01 | 2026-08-31 | 122 | 51, 39